## Sheet1
Project X - Automated Attendance System
Start Date: March 04, 2025 |  |  |  | DEADLINE: MAY 02, 2025 |  |  | Days Left: -16 days |  |  | Task Done: 25 / 26 (96.15%)
Task ID | Task Name | Sub Task ID | SubTask Name | Deliverables | Assignee | Estimated Hours (days) | Plan Start Date | Plan End Date | Actual Start Date | Actual End Date | Status
1 | Project Initiation | 1.1 | Project Kickoff Meeting |  | Roberto Prisoris | 10 | 2025-03-04 | 2025-03-04 | 2025-03-04 | 2025-03-04 | Done
|  | 1.2 | Identifying Project Scope & Objectives | Updated Requirements Review | Jenny Babe Arac | 10 | 2025-03-05 | 2025-03-05 | 2025-03-06 | 2025-03-06 | Done
2 | Requirement Analysis | 2.1 | Gather Functional Requirement | Project X - Client Stated Requirement | Kit Adrian Diocares | 2 | 2025-03-06 | 2025-03-06 | 2025-03-07 | 2025-03-07 | Done
|  | 2.2 | Initiate an Elicitation Session with Client | Project X - Requirements Elicitation - v.1.0 | Shannen Mendoza | 2 | 2025-03-06 | 2025-03-06 | 2025-03-11 | 2025-03-11 | Done
|  | 2.3 | Validate Requirements with Client | Project X - Requirements Elicitation - v.1.1 | Jenny Babe Arac | 2 | 2025-03-06 | 2025-03-06 | 2025-03-12 | 2025-03-12 | Done
|  | 2.4 | Finalizing System Requirements | Project X - Requirements Elicitation - v.1.2 | Shannen Mendoza | 2 | 2025-03-06 | 2025-03-06 | 2025-03-12 | 2025-03-12 | Done
3 | High-Level Design | 3.1 | Conceptual Design | High-Level Use Case Diagrams, Conceptual Model Requirement Diagrams Project Plan | Kit Adrian Diocares, Roberto Prisoris, Jenny Babe Arac | 12 | 2025-03-07 | 2025-03-08 | 2025-03-14 | 2025-03-14 | Done
|  | 3.2 | Revised Deliverables | Project Plan Traceability Matrix | Team A | 5 | 2025-03-10 | 2025-03-10 | 2025-03-21 | 2025-03-21 | Done
4 | Detailed Design | 4.1 | Develop Class Diagram | Class Diagram with Attributes & Methods | Kit Adrian Diocares | 5 | 2025-03-11 | 2025-03-11 | 2025-03-21 | 2025-03-21 | Done
|  | 4.2 | Sequence Diagram | Detailed Sequence Diagram | Shannen Mendoza | 3 | 2025-03-11 | 2025-03-11 | 2025-03-20 | 2025-03-20 | Done
|  | 4.3 | Activity Diagram | Activity Diagrams for Key System Processes | Jenny Babe Arac | 3 | 2025-03-12 | 2025-03-12 | 2025-03-20 | 2025-03-20 | Done
|  | 4.4 | Prototyping | Figma Link | Team A | 28 | 2025-03-13 | 2025-03-15 | 2025-03-18 | 2025-03-28 | Ongoing
5 | Documentation & Version Control | 5 | Set up Version Control (Git) | Git Repository Setup Provide Access to Repository | Roberto Prisoris | 2 | 2025-03-17 | 2025-03-17 | 2025-03-14 | 2025-03-14 | Done
6 | Agile Development Process | 6.1 | Sprint Planning | Sprint Backlog Development Roadmap | Roberto Prisoris | 5 | 2025-03-17 | 2025-03-17 | 2025-03-28 | 2025-03-20 | Done
|  | 6.2 | Daily Standups | Recording Progress Updates | Kit Adrian Diocares | 5 | 2025-03-18 | 2025-03-18 | 2025-03-05 | 2025-04-05 | Done
|  | 6.3 | Sprint Demonstration to Client | Sprint Review, Working Feature Demostration | Jenny Babe Arac | 8 | 2025-03-19 | 2025-03-19 | 2025-03-10 | 2025-04-15 | Done
7 | Test-Driven Development (TDD) | 7 | Develop & Test a Module using TDD | Test Cases, Unit Tests TDD Implementation | Roberto Prisoris | 200 | 2025-03-20 | 2025-04-08 | 2025-04-10 | 2025-04-15 | Done
8 | Implementation | 8.1 | Develop Authentication | Secure API, OTP Authentication, QR Validation | Roberto Prisoris | 25 | 2025-04-09 | 2025-04-11 | 2025-04-05 | April 10, 2025 | Done
|  | 8.2 | Implement Role-based Access Control | Admin, Instructor, Student Access System | Kit Adrian Diocares | 15 | 2025-04-14 | 2025-04-15 | 2025-04-02 | 2025-04-12 | Done
|  | 8.3 | Attendance Tracking Features | QR Code Scanner, GPS Validation | Roberto Prisoris | 20 | 2025-04-16 | 2025-04-17 | 2025-04-03 | April 8, 2025 | Done
|  | 8.4 | Cloud Database Integration | Hosted Database, Secure APIs | Jenny Babe Arac | 15 | 2025-04-18 | 2025-04-19 | 2025-04-10 | April 14, 2025 | Done
9 | Testing & Validation | 9.1 | Unit Testing | Verified Functionality of Individual Components | Shannen Mendoza | 48 | 2025-04-21 | 2025-04-25 | 2025-04-06 | 2025-04-15 | Done
|  | 9.2 | System Testing | Full System Integration Test | Shannen Mendoza | 8 | 2025-04-28 | 2025-04-28 | March 28, 2025 | April 1, 2025 | Done
|  | 9.3 | User Acceptance Testing (UAT) | Client Validation & Feedback | Jenny Babe Arac | 5 | 2025-04-29 | 2025-04-29 | 2025-04-02 | 2025-04-20 | Done
10 | Final Demonstration & Handover | 10.1 | Final System Review | Working Code, Documentation, User Manual | Kit Adrian Diocares | 5 | 2025-04-30 | 2025-04-30 | 2025-03-06 | May 19, 2025 | Done
|  | 10.2 | Final Presentation | Project Presentation, Live Demo | Team A | 5 | 2025-05-01 | 2025-05-01 |  |  | Done
Formulas:
Plan Start Date = WORKDAY([Plan End Date, row above], IF(SUMIF(I4:[Plan End Date, row above], [Plan End Date, row above], G4:[Estimated Hours (days), row above]) + [Estimated Hours (days)] <= 8, 0, 1))
Plan End Date = [Plan Start Date] + CEILING([Estimated Hours (days)]/10,1)-1